🛡️ SAMS

Software Requirements Specification & Business Requirements Document

Implementation Plan

แผนการพัฒนาและการนำไปใช้งาน — โมดูล QA

| รายการ | รายละเอียด |
| --- | --- |
| Document No. | SAMS-QA-SRS-12 |
| Module | Quality Assurance (QA) |
| เวอร์ชัน | 1.0 |
| วันที่จัดทำ | 2026-04-27 |
| จัดทำโดย | Triple-T Development Team |
| อนุมัติโดย | _(รอลงนาม)_ |
| สถานะ | Draft |

# Revision History

| เวอร์ชัน | วันที่ | ผู้จัดทำ | รายละเอียดการเปลี่ยนแปลง |
| --- | --- | --- | --- |
| 1.0 | 2026-04-27 | Triple-T Development Team | ร่างแรก — สร้างจาก codebase + เอกสารอ้างอิง SAMS |

# 1. Project Overview

## 1.1 Phasing Strategy

📊 [ Diagram: 3-Phase Roadmap ] (ดูแผนภาพ Mermaid ในไฟล์ .md — graph LR — Phase 1 (3mo) → Phase 2 (3mo) → Phase 3 (TBD))

## 1.2 Phase Scope Summary

| Phase | ระยะเวลา | Scope | Go-Live |
| --- | --- | --- | --- |
| Phase 1: Core MVP | 3 เดือน | Staff/Auth/Monitor/Dashboard + RBAC + Audit + Notification | M+3 |
| Phase 2: Enhancement | 3 เดือน | Course Mgmt + Scheduler advanced + CAAT + Reports | M+6 |
| Phase 3: Advanced | TBD | Mobile + Customer API + AI + Multi-tenant | TBD |

# 2. Phase 1 Plan (3 เดือน)

## 2.1 Phase 1 Timeline

📊 [ Diagram: Phase 1 Gantt Chart ] (ดูแผนภาพ Mermaid ในไฟล์ .md — gantt — Setup/Backend/Frontend/Test/Deploy across 13 weeks)

## 2.2 Phase 1 Deliverables

| Deliverable | Owner | Due |
| --- | --- | --- |
| Requirements workshop minutes | PM | Week 2 |
| API contract (OpenAPI spec) | Architect | Week 4 |
| Database migration scripts | Backend | Week 6 |
| Working Staff module | FE+BE | Week 8 |
| Working Authorization module | FE+BE | Week 10 |
| Working Dashboard | FE+BE | Week 11 |
| RBAC + Audit + Notification | FE+BE | Week 11 |
| UAT package + scripts | QA | Week 11 |
| Production deployment | DevOps | Week 13 |

## 2.3 Phase 1 Sprint Breakdown

| Sprint | Focus | Critical Output |
| --- | --- | --- |
| Sprint 1 (W1-2) | Setup + Workshop | Requirements doc, environment ready |
| Sprint 2 (W3-4) | Architecture + DB schema | ER + Migration script |
| Sprint 3 (W5-6) | Auth + RBAC | Login + permission middleware |
| Sprint 4 (W7-8) | Staff Module | Full CRUD working |
| Sprint 5 (W9-10) | Authorization Module | Lifecycle + CRS calc |
| Sprint 6 (W11-12) | Monitoring + Dashboard + Polish | Auto-alerts, audit, reports |
| UAT/Deploy (W13) | UAT, fix, deploy | Production live |

# 3. Team Structure

## 3.1 Phase 1 Team

📊 [ Diagram: Team Org Chart ] (ดูแผนภาพ Mermaid ในไฟล์ .md — graph TB — PM/BA/Architect → FE/BE/QA/DevOps)

## 3.2 Roles & Responsibilities

| Role | Count | Responsibilities |
| --- | --- | --- |
| Project Manager | 1 | Schedule, risk, communication |
| Business Analyst | 1 | Requirements, workflow, UAT facilitation |
| Architect / Tech Lead | 1 | Architecture, code review |
| Frontend Developer | 2 | UI, integration |
| Backend Developer | 2 | API, database, services |
| QA Engineer | 1 | Test plan, automation, manual UAT |
| DevOps Engineer | 0.5 (shared) | CI/CD, deployment |
| UX Designer | 0.5 (shared) | Wireframes, design review |

## 3.3 RACI Matrix

| Activity | PM | BA | Arch | FE | BE | QA | DevOps | Stakeholder |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Requirements gathering | A | R | C | I | I | I | I | C |
| Architecture design | I | C | R | C | C | C | C | I |
| API contract | I | C | A | C | R | C | I | I |
| Frontend dev | I | I | C | R | C | C | I | I |
| Backend dev | I | I | C | C | R | C | I | I |
| Unit/Integration test | I | I | I | R | R | C | I | I |
| UAT | C | A | I | I | I | R | I | C |
| Deployment | A | I | C | C | C | C | R | I |

⚠️ หมายเหตุ: R=Responsible, A=Accountable, C=Consulted, I=Informed

# 4. Phase 2 Plan (3 เดือน, M+3 ถึง M+6)

## 4.1 Phase 2 Scope

📊 [ Diagram: Phase 2 Scope Map ] (ดูแผนภาพ Mermaid ในไฟล์ .md — graph LR — Course/Scheduler/CAAT/Reports/Self-Service/MFA)

## 4.2 Phase 2 Timeline

📊 [ Diagram: Phase 2 Gantt Chart ] (ดูแผนภาพ Mermaid ในไฟล์ .md — gantt — Course/Scheduler/Integration/MFA across 12 weeks)

# 5. Phase 3 Plan (TBD)

| Feature | Trigger Condition |
| --- | --- |
| Mobile Native App | User feedback ขอ + budget approve |
| Customer Webhook API | Customer airline พร้อมรับ |
| AI Competency Prediction | Data 2+ ปีพร้อม + business case |
| Multi-tenant | มี MRO อื่นต้องการใช้ |

# 6. Migration Strategy

## 6.1 Data Migration Plan

📊 [ Diagram: Migration Flow ] (ดูแผนภาพ Mermaid ในไฟล์ .md — flowchart TD — Profiling → Script → Dry-run → UAT → Production → Validation)

## 6.2 Migration Checklist

| Item | Owner | Status |
| --- | --- | --- |
| Excel data profiling | BA | Pre-Sprint 5 |
| Migration script ready | BE | Sprint 6 |
| Staging environment loaded | DevOps | Sprint 6 |
| Dry-run executed | BE+QA | Sprint 7 (W11) |
| Validation report reviewed | BA+QA | Sprint 7 (W11) |
| UAT users approve | Stakeholder | Sprint 8 (W12) |
| Production migration scheduled | DevOps | Sprint 8 (W12) |
| Cut-over plan documented | PM | Sprint 8 (W12) |
| Rollback plan tested | DevOps | Sprint 8 (W12) |

# 7. Cut-over & Go-Live Plan

## 7.1 Go-Live Day Timeline (Saturday)

| เวลา | Activity | Owner | Duration |
| --- | --- | --- | --- |
| 22:00 (Fri) | Notification ส่ง user | PM | — |
| 22:00 | Final Excel export from old system | BA | 2 ชม. |
| 00:00 (Sat) | Database migration start | BE+DevOps | 4 ชม. |
| 04:00 | Validation report | QA | 1 ชม. |
| 05:00 | Smoke test on production | QA+BA | 2 ชม. |
| 07:00 | Manager approval | PM | 1 ชม. |
| 08:00 | Open system to users | DevOps | 30 min |
| 08:00 - 18:00 | Hypercare onsite (Day 1) | All | — |

## 7.2 Rollback Triggers

| Condition | Action |
| --- | --- |
| Migration validation fail (>1% error) | Stop, investigate, restore backup |
| Critical bug in Smoke test | Rollback, fix in QA env, retry |
| Performance < target (>5x slower) | Rollback, performance tuning |
| Security incident detected | Rollback immediately |

## 7.3 Hypercare (2 weeks post Go-Live)

📊 [ Diagram: Hypercare Phases ] (ดูแผนภาพ Mermaid ในไฟล์ .md — graph LR — Go-Live → Week 1 (on-site daily) → Week 2 (standby) → Normal Support)

# 8. Resource & Cost Estimation

## 8.1 Effort Estimation (Phase 1)

| Role | Person-weeks |
| --- | --- |
| PM | 13 |
| BA | 10 |
| Architect | 8 |
| Frontend Dev (× 2) | 24 |
| Backend Dev (× 2) | 24 |
| QA Engineer | 8 |
| DevOps (shared) | 4 |
| UX Designer (shared) | 4 |
| Total | 95 person-weeks |

## 8.2 Infrastructure Cost

- Production servers (FE × 2, BE × 2)

- Database (Primary + backup)

- File storage (100 GB initial)

- Monitoring tools

- Email service (10K/month)

- SSL certificate

⚠️ หมายเหตุ: ตัวเลขอ้างอิงในเอกสารสัญญา

# 9. Communication Plan

## 9.1 Communication Cadence

| Meeting | Frequency | Audience | Duration |
| --- | --- | --- | --- |
| Daily Standup | Daily | Dev team | 15 min |
| Sprint Planning | Bi-weekly | Dev + BA + PM | 2 hr |
| Sprint Review | Bi-weekly | Dev + BA + PM + Stakeholder | 1 hr |
| Sprint Retro | Bi-weekly | Dev + PM | 1 hr |
| Stakeholder Update | Weekly | PM + Stakeholder | 30 min |
| Steering Committee | Monthly | PM + Sponsors | 1 hr |
| Architecture Review | Bi-weekly | Architect + Tech leads | 1 hr |

## 9.2 Communication Channels

| Channel | Use |
| --- | --- |
| Slack/Teams | Day-to-day chat |
| Jira/Trello | Task tracking |
| Confluence | Documentation |
| Email | Formal sign-off |
| Video call | Meetings |

## 9.3 Escalation Path

📊 [ Diagram: Escalation Flow ] (ดูแผนภาพ Mermaid ในไฟล์ .md — graph TD — Dev → Architect/PM → Steering → Sponsor)

# 10. Risk Management Plan

⚠️ หมายเหตุ: รายละเอียด Risk เต็มอยู่ใน SRS-13

## 10.1 Risk Mitigation Calendar

| Sprint | Risk Focus | Action |
| --- | --- | --- |
| Sprint 1-2 | Process mismatch (OR-03) | Workshop + prototype review |
| Sprint 3-4 | Performance (TR-04) | Database design review |
| Sprint 5-6 | Migration risk (OR-01) | Data profiling + dry-run prep |
| Sprint 7-8 | UAT engagement (OR-05) | Stakeholder commitment |
| Pre Go-Live | Security (TR-03) | Pen-test + security audit |

## 10.2 Contingency Buffer

| Phase | Plan | Buffer |
| --- | --- | --- |
| Phase 1 | 12 weeks | +2 weeks (16% buffer) |
| Phase 2 | 12 weeks | +2 weeks |
| Migration | 1 weekend | +1 weekend rollback option |

# 11. Quality Gates

## 11.1 Sprint-level Gates

| Gate | Criteria |
| --- | --- |
| Definition of Ready (DOR) | Story has acceptance criteria + estimated |
| Definition of Done (DOD) | Code + Test + Code review + Deploy to Dev |
| Sprint Review | Demo to PM/Stakeholder, accept or backlog |

## 11.2 Phase Gate (Pre Go-Live)

| Criterion | Threshold |
| --- | --- |
| All P0/P1 features delivered | 100% |
| Code coverage | ≥ 70% |
| All P0 test cases pass | 100% |
| Security audit | No Critical findings |
| Performance test | All NFR met |
| UAT sign-off | All key stakeholders |
| Documentation | Complete (architecture, API, runbook) |
| Migration tested | Dry-run + validation pass |

# 12. Training & Change Management

## 12.1 User Training Plan

| Audience | Format | Duration | Materials |
| --- | --- | --- | --- |
| QA Manager | Workshop + hands-on | 4 hours | User manual + recorded session |
| Trainer | Workshop + hands-on | 3 hours | User manual + recorded session |
| CM Officer | Workshop + hands-on | 3 hours | User manual + recorded session |
| Inspector | Brief + self-study | 1 hour | User manual |
| CS / AME | Brief | 30 min | Quick guide |
| Admin | Workshop + hands-on | 4 hours | Admin guide |

## 12.2 Change Management

📊 [ Diagram: ADKAR Model Flow ] (ดูแผนภาพ Mermaid ในไฟล์ .md — graph LR — Awareness → Desire → Knowledge → Ability → Reinforcement)

# 13. Post Go-Live Support

## 13.1 Support Tiers

| Tier | Description | SLA |
| --- | --- | --- |
| Tier 1 | User questions, basic troubleshooting | < 4 hours |
| Tier 2 | Bug reproduction, configuration | < 1 day |
| Tier 3 | Code fixes, deep investigation | < 1 week (Major) |

## 13.2 Continuous Improvement

| Activity | Frequency |
| --- | --- |
| User feedback survey | Quarterly |
| Performance review | Monthly |
| Security review | Quarterly |
| Feature backlog grooming | Monthly |
| Stakeholder business review | Quarterly |

# 14. Critical Path Summary

📊 [ Diagram: Critical Path Diagram ] (ดูแผนภาพ Mermaid ในไฟล์ .md — graph LR — Workshop → DB+Auth → Auth Module → Migration → UAT → Go-Live)

⚠️ หมายเหตุ: Critical path = ลำดับนี้ห้าม slip; กิจกรรมอื่น parallel ได้

# 15. Success Criteria

## 15.1 Phase 1 Success Criteria

| Criterion | Target |
| --- | --- |
| ✅ All P0 features delivered | 100% |
| ✅ All P1 features delivered | ≥ 95% |
| ✅ UAT sign-off obtained | All stakeholders |
| ✅ User adoption (active rate) | ≥ 80% by Day 30 |
| ✅ Compliance % accuracy | 100% match Excel baseline |
| ✅ System uptime (post Go-Live) | ≥ 99.5% |
| ✅ User satisfaction | ≥ 4.0 / 5.0 |
| ✅ Critical bugs in production | 0 |

## 15.2 Long-term Success Metrics (M+6)

| Metric | Baseline | Target M+6 |
| --- | --- | --- |
| CM Officer time on expiry checks | 2-3 days/month | < 4 hours/month |
| Authorization processing time | 1-2 days | < 1 hour |
| Compliance % data accuracy | unknown | 100% |
| Audit prep time | 2 weeks | 2 days |
| User satisfaction | n/a | ≥ 4.5 / 5.0 |

— จบเอกสาร SAMS-QA-SRS-12 —

สร้างโดย Triple-T Development Team | SAMS QA Module SRS/BRD v1.0